## Test Approach
S/No | Task/Activity | #Hours | #MD | Remarks
| Test Phase - SIT |  |  | Assume 1 Week of SIT
1 | Test Planning & Design
2 | Requirement System & FSD Walkthrough /Discussion
3 | Develop Test Strategy / Plan (Review & Revise)
4 | Develop SIT Test Condition & cases (develop, review and revise)
5 | Data Requirement definitions & creation
6 | Test Environment Requirements, Setup and configurations
7 | Test Management, co-ordination and defect management
8 | Test Execution(including Retest) |  |  | 20% Defect Rate
9 | Regression Test |  |  | Regression of critical functions and major defects from first round of testing
10 | Test Reporting ( Daily Test Status Report)
| Test Phase - UAT |  |  | Assume 1 week UAT
Test Execution (UAT Defects Retest)
Assumptions
1 | All third party systems are working and linked with the new flight booking system developed.
2 | Payment system integrated with the flight booking system
3 | Able to create own test data in sandbox testing environment

## High Level Scenaraios
| High Level Test Scenarios | No of Test Cases
1 | Login verification
2 | Guest user complete booking of tickets process
3 | Registration of guest details process
4 | Registered user complete booking tickets process
5 | Global Dist system validation process
Global dist system Validation process without booking date entered
Global dist system validation process with past booking date entered
Global dist system validation process with same departure and arrival airports
6 | boundary value analysis for 24 hrs payment process
Registered user immediate payment process
Registered user payment within 24 hrs
Registered user payment after 24 hrs
Guest user immediate payment process
Guest user payment within 24 hrs
Guest user payment after 24hrs
7 | valid email process
8 | invalid email process